## Sheet1
Number | Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Database fails | MySQL Crashes | Low | High | MySQL/Computer | Use the schema to recreate the database | Keep schema ready at hand and create a backup of the database
2 | Broken version deployed onto production | Deployed product may have issues or missing requirements | Medium | High | Developer (Me) | Revert production to most recent stable version | Do testing before any deployments
3 | Requirements not being upheld | The requirements are not available on the application | Medium | High | Developer (Me) | Keep track of my goals on JIRA and check with Aswene if the goals are being met | Ensure all requirements are set out and measured compared to the specification. Also ensure I measure the scope of the project.
4 | Github branches remove code | New feature branches get replaced and lost | Medium | High | Developer (Me) | Ensure the branches are always merged onto Dev once completed and dev is always pulled to capture the latest updates | Adhere to the priniciples of branching and make sure to cover all merges carefully